## Cover Page
SCHEDULE OF WORKS
Site: | 7 Dering Street, Mayfair, London W1S 1AE
Job: | Replacement of the entrance portal,
Roofs repairs, Refurbmishment and Internal Remodeling
Job Ref: | 2001-1238-SCH

## 0
00. preliminaries, site office and scaffolding
0.1 | Introduction
0.1.1 | The works listed below shall constitute the Employers Requirements for the Replacement shopfront, internal alterations, refurbishment and associated works at the following address:
7 Dering Street, Mayfair, London W1S 1AE
0.1.2 | The Employer shall be Embassy of the Republic of Serbia - London
0.1.3 | The Employer is seeking to enter into Contract at the earliest opportunity after the return of Tenders, with a preferred start within 6 weeks of selection of the preferred tender.
Tenderers are requested to confirm their anticipated programme and timetables.
0.1.4 | The site will remain unoccupied for the duration of the works. The contractor shall be responsible for organizing the insurance of the works.
0.1.5 | This Schedule of Works is to be read in conjunction with the drawings which together will form the contract documents:
STS Structural Engineering ltd Drawings: 2001-1238-101 to 111, Rev.B
This Schedule of Works
0.1.6 | The Employer has secured Planning Consent for the works from the local council
0.1.7 | In pricing this documentation the Contractor will raise to the attention of the Employers agent any conflicting information between any of the parts of any of the Tender documents and drawings.
The contractor shall ensure that all parts of the documentation are priced whether they be referenced on only drawings or only in this schedule or in both.
0.1.8 | Contractors may visit the site by prior arrangement by contacting Counsellor Mr Vladimir Disovic:
07542 291884
0.2 | Preliminaries
0.2.1 | The Contractor may use the Employer’s electricity and water supply as reasonable necessary in connection with the carrying out of the works. The contractor shall inspect the available power supply within the property to confirm that it is adequate for their requirements.
0.2.2 | Noise: Working hours are to be agreed beforehand and with the Employer and must comply with the requirements of the Local Authority, but may be assumed to be from 07.30hrs until 17.00hrs.
The appointed contractor must be mindful that the adjacent properties are occupied and to ensure no undue disturbance to the neighbouring properties.
0.2.3 | The identification of existing statutory or otherwise services and arrangements for connection or disconnection (as necessary) is to be the responsibility of the contractor.
0.2.4 | Contractor welfare facilities: the contractor must arrange for temporary WC. At the end of each working day, the facilities are to be left in a clean condition.
0.2.5 | Terms and Conditions: The terms and conditions of the contract will be those set in the STS custom short building contract (form of contract available upon request)
0.2.6 | Any provision for skips and their licenses are to be the responsibility of the contractor and associated costs are to be included in the Tender price.
0.2.7 | Liaison with the Local Authorities and utilities is to be the responsibility of the contractor.
0.2.8 | Materials and workmanship generally. All works are to be inspected on a regular basis by the Employer.
Good Practice: where and to the extent that materials, products and workmanship are not fully detailed or specified they are to be of a standard appropriate to the works and suitable to the purposes stated in, or reasonably inferred from the project documents and in accordance with good building practice.
0.2.9 | The appointed contractor will make arrangements for all site operatives working on site to be made known to the Employer and will confirm contact details for use in the event of an emergency.
0.2.10 | The contractor shall take all necessary measures to prevent damage to the external pavement. The contractor shall allow for nominal repairs to the pavement due to normal use of the site. Any undue damage shall be made good by the contractor, and it is his responsibility to ensure that the pavement remains undamaged as far as reasonably possible.
0.3 | Electrical Installation
0.3.1 | The installation shall comply with the relevant standards of good practice and workmanship generally acknowledged by the industry.
All labour shall be qualified by trade test (where applicable) or shall be of an accepted grade for the particular works.
0.3.2 | All materials shall be new, of good quality and manufactured or fabricated to comply with the current requirements of the relevant British Standards specification as a minimum.
0.3.3 | The entire works shall be executed in accordance with the current edition of the ‘Regulations for the Electrical Equipment of Buildings’ and any amendments issued by the Institution of Electrical Engineers.
0.3.4 | The position of all power points and equipment shall be as shown on accompanying drawings. If in doubt the contractor is to inform the Employer.
0.3.5 | Segregation of services. The contractor shall be responsible for determining the ducts and pipe runs of all other services prior to carrying out the electrical installation. All electrical cables, conduits and accessories shall be installed with a minimum clearance of 150mm from non-electrical services.
0.3.6 | The contractor shall be responsible for coordinating all his services with those of the utilities companies.
0.3.7 | Wiring and accessories: wire in pvc/ pvc twin earth cables concealed in the ceiling. Builders HIP conduit in walls to socket positions. Minimize the number of joints.
0.3.8 | The contractor is to provide the Employer or his agent, with 1no. copy of all test certificates for the entire electrical installation undertaken as part of these works as required by the Building Regulations current at the time of tender.
0.4 | Heating and H&C Water Installation
0.4.1 | The heating system installation is to be designed and installed by the contractor and is to be fit for purpose producing minimum water pressure compliant with applicable regulations - notably the gas installation act 1974. The contractor or subcontractor is to be Corgi Registered or equivalent and to provide 1no. copy to the Employer of certification as required by the Building Regulations at the time of tender.
0.4.2 | Flue Systems: Flue from the boiler to a wall terminal as supplied by the boiler manufacturer. It is assumed that the new flue outlet will be adjacent to the boiler location; to be agreed with the Employer.
0.4.3 | All pipe work in copper tube BS 2871 with solder joints. All routes to be agreed beforehand.
0.4.4 | Insulate all heating or hot water pipe work where concealed. All joints sealed with aluminium foil tape.
0.4.5 | The controls for the heating are to include flow thermostat, 7-day time clock with day omission, 2 channels (heating and hot water). The contractor is to allow for the Employer to witness the operation of the heating, hot water systems before practical completion.
0.4.6 | Two weeks before practical completion the contractor is to provide the following :
Copies of all test certificates, manufacturer’s warranties and guarantees, operating instructions and emergency procedures.
0.5 | Public Health, Drainage Installation
0.5.1 | It is assumed that all existing drainage systems can be utilised. The contractor is to take care when working in close proximity to all existing drainage systems, taking care not to block or allow any debris to enter.
0.5.2 | Prior to commencement of the works the Contractor is to assess the method of connection to the existing underground drainage.
0.5.3 | The main kitchen appliances will be supplied by the Employer for fitting by the Contractor (refer to Section 07) and connection to the existing systems. Contractor to inform the Employer once drainage runs are flowing freely, in good working order etc.
All concealed drainage pipes in plastics. Drainage: 75mm deep seals to bottle traps to sink. Sink waste size to be 40mm.
0.5.4 | Routes of pipe work to be as indicated on the drawings or as agreed with the Employer in advance of installation.
0.6 | Site offices, Scaffolding and Temporary Works
0.6.1 | Provide scaffolding to the building as required to reconstruct the roof, install doors and windows, repair the façade etc if necessary.
0.6.2 | Provide all necessary site supervision, office management, administration, insurances, protection, welfare, plant, tools, etc. and health and safety compliance for the safe and proper execution of the works - for the duration of works.
0.6.3 | Clean up all the floors, windows, stairwell, etc., as well as remove all the rubbish from the site, prior to commissioning
Summary of Costs by Section
Section No. |  | Total
0 | Preliminaries, Site Office and Scaffolding
1 | Demolitions
2 | Basement floor Insulation, Tanking, Screed
3 | Walls and Partitions
4 | Floors, Roofs, Ceilings and Stairs
5 | Fittings, Finishes and Equipment
6 | Windows and Doors
7 | Services
8 | Additional Items specified by the contractor:
Total Construction Cost
VAT@20%:
Total value of the contract incl. VAT:
Provisional Items:
Contingency:

## 1
01. demolitions
Item | Element | Description | Cost
1.1 | General | Allow for carting away of materials arising from demolitions, excavation, strip out, breaking out etc. Generally allow for the temporary storage of materials and removal from the site (skips)
To protect the special architectural or historic interest of this listed building. You must not disturb existing ornamental features including chimney pieces, plasterwork, architraves, panelling, doors and staircase balustrades. You must leave them in their present position unless changes are shown on the approved drawings or are required by conditions to this permission. You must protect those features properly during work on site.
All new work and improvements inside and outside the building must match existing original adjacent work in terms of the choice of materials, method of construction and finished appearance.
Demolitions:
1.2 | Removal of the existing floor finish elements | Allow for removal and carting away of the existing floor tiles throughout and dispose of materials. Break out material, remove and cart away as required. The existing floor boards are to be retained and be bolted down into the existing joists. Each floor board is to be inspected for rot and damage, and any damaged floor boards are to be replaced with new timber floor boards like-for-like.
Allow for removal of the existing timber decking on the ground floor
Allow for removal and carting away of the existing wood flooring and carpets throughout.
1.3 | Existing Walls | Remove sections of the existing loadbearing and non-loadbearing walls and partitions including removal of both solid and timber framed walls as shown in the drawings. Allow here for removing of all wall plastering throughout the whole building.
1.4 | Existing ceilings | Allow here for removing of all plaster ceiling throughout the building.
Allow for removal and carting away the existing loft ceiling joists and insulation as and where specified in the drawings. Break out material, remove and cart away as required.
1.5 | Doors | Remove all of the existing doors and dispose off-site (as specified in the drawings).
1.6 | Windows | Remove all the windows (icl. entrance portal on the ground floor) as specified in the drawings and carefully dispose off-site for re-use.
1.7 | Removal of the existing skylights | Allow for removal of the existing skylights, all as specified in the drawings - this should be safely removed and stored off-site.
1.8 | Existing pitched and flat roofs | Allow for removal and carting away of the existing segment of the roofs (insulation and covering) as specified in the drawings or storage for re-use if applicable. All roof timbers to be carefully inspected for rot and damage. Where possible, the localised damage to the timbers will be made good by gluing in new timber elements. Where the entire timbers are beyond repair, they will be replaced like-for-like.
1.9 | Removal of the existing kitchen elements | Allow for removal of the existing kitchen elements. Allow for breaking up of the material, temporary storage and removal of the material from site (skips).
1.10 | Removal of the existing sanitary ware | Strip out all existing sanitaryware, remove pipework and and strip existing tiles as required. Allow for removal from site.
1.11 | Removal of the existing radiators and air conditioning units | Remove all the existing radiators and air conditioning units in the entire building.
1.12 | Removal of the existing service unit (rear elevation) | Allow for removal and carting away of the existing service unit to the back of the building
1.13 | Gas | All existing gas services shall be identified, adequately protected and clearly marked for the duration of the works.
1.14 | Water and electricity | The contractor shall make use of the existing water and electricity supply for the duration of the works as stated above. He shall arrange for suitable connections to be made from the main distribution board as per his requirements.
Total |  | Total demolitions carried to summary

## 2
02. basement insulation, tanking, screed
Item | Element | Description | Cost
2.1 | General | The tanking is to be comprised of a (Newton or similar) system installed internally to the basement. The tanking system to be designed, detailed, installed, tested and commisioned by a specialist tanking company. The tanking contractor to provide a suitable minimum 15 year guarantee covering both the tanking system and the entire basement extension.
2.2 | Basement | Allow for the installation of a drained tanked system - Newton or similar. Drainage system to be installed by a competent specialist sub-contractor. Contractor to provide minimum 15 years guarantee for the drainage system! System to comprise vertical and horizontal, tanking, drainage channels, and two pairs of pumps with alarm within the previously created sump, as well as the required discharge routes.
2.3 | Existing Basement Slab | Closed cell polystirene basement floor slab insulation over DPC - please see drawings for more information.
2.4 | Existing Basement Slab | 65mm unbonded float finish screed to be laid on insulation. Allow for mesh reinforcement to the screed as indicated in the drawings.
Total |  | Basement floor Insulation, Tanking, Screed

## 3
03. Walls and partitions
Item | Element | Description | Cost
N.B. Basement floor insulation included in section 02 of the Schedule of Work
3.1 | Basement walls | All basement walls to be lined with metal studwork, insulated as specified in the drawings. Studwork to be lined with plasterboard, bonded and skimmed to prepare for decoration. Provide a lump sum to include studwork, insulation, plasterboard, etc.
3.2 | Fire protection for the existing steel elements | 1 hour Fire Resisting Casing To Existing Structural Steelwork. Typically provide 2 layers fireproof plasterboard all around the beams.
3.3 | Existing Building | Provide wall replastering to the entire building.
3.4 | Existing Building-Repairs | Allow for Resin Bonded Galvanized Steel Bars (Helifix or similar) for crack repairs as shown in the building regulations drawings
3.5 | Dry-lining of solid walls | Plasterboard dry-lining of existing walls. Walls to be faced with 9.5 or 12.5mm single layer plasterboard on dabs. Allow for vapour-control plasterboard in the Kitchens, toilets and utility. Plasterboard to be fully bonded, with associated beads and stops and prepared for decoration. Allow here for two coats finish plaster.
3.6 |  | Allow for patch repairs to the plaster following the insertion of new door and window frames.
3.7 | Internal stud walls | New internal stud framed non-loadbearing partitions throughout to include the following items:
3.7.1 |  | Studwork for non-loadbearing partitions Softwood Studding For Partitions @600mm c/c w. associated wall plates to include for noggings as required.
3.7.2 |  | Studwork for the Loadbearing walls. Softwood Studding For Partitions @400mm c/c w. associated wall plates to include for noggings as required.
3.7.3 |  | M20a 12.5mm Single Vapour-Control Layer Plasterboard (For Kitchen, Toilets and Utility) Backings Nail Fixed.
3.7.4 |  | 2 Layers sound block 15mm Plasterboard with joints staggered fixed to the studwork via resilient bars for all separating partitions where specified in the drawings.
3.7.5 |  | Allow here for plywood lining in locations where sanitary ware and utility cupboards are to be fixed.
3.7.6 |  | M20a Two Coat Board Finish Plaster
3.7.7 |  | M20a Beads And Stops For Plaster at all external angles and stop ends
3.7.8 |  | Allow for doubled-up joists/trimmers under all new partitions running parallel to the span of the joists.
Total |  | Total walls and partitions carried to summary

## 4
04. floors, roofs, ceilings and stairs
Item | Element | Description | Cost
4.1 | Existing Ground floor slab | 65mm unbonded float finish screed to be laid on ground floor slab. Allow for mesh reinforcement to the screed as indicated in the drawings. Floor level to be raised to be leveled with the existing hallway.
4.2 | Flat Roofs | Existing flat roof joists to remain if adequate. Allow for all the associated doubled-up rafters, trimmers, noggings and blockings if required.
4.2.1 |  | Allow for all the layers as specified in the drawings, including firrings, insulation, sarking boards, cover materials, etc. Refer to construction notes.
4.2.2 |  | Allow here for roof and wall ties, roof straps, joist hangers and other associated fixings, etc.
4.3 | Pitched Roofs | Remove all existing roof tiles and safely store on-site for re-use. Any broken or demaged roof tiles to be replaced with new roof tiles to closely match the existing. Where the existing roof timbers (rafters, hip-beams, ridge board and wall plates) have been demaged, new timbers shall be provided spliced to existing. Provide new insulation, breather membrane and ceiling plasterboard all as indicated in the building regulations drawings. Refer to construction notes.
4.3.1 |  | Allow here for roof and wall ties, roof straps, rafter hangers and other associated fixings, etc. if required.
4.4 |  | Flashings, Fascia's, etc. For the Roofs
4.4.1 |  | Provide all the flashings and guttering as required.
4.4.2 |  | Provide GRP, zinc or lead valley gutters where required.
4.4.3 |  | Provide Zinc upstand flashing/trims to all SVP, duct and roof hatch and as required.
4.4.4 |  | Two Coats of Patination Oil To Lead Features And Flashings
4.4.5 |  | Allow for replacement of all existing downpipes. Provide lump sum price for uPVC Rainwater Goods including box-gutters, downpipes, etc.
4.5 | Ceilings
4.5.1 | Basement ceiling | New suspended ceiling to the basement - Allow for the required framing, plasterboard, beads and stops, etc. Please see drawings for more information. Allow for the basement services to be boxed-in as necessary. Please see drawings for more information.
4.5.2 | Upper Floors | Allow for suspended ceiling as specified in the drawings. Allow for the required framing, plasterboard, beads and stops, etc.
4.5.3 |  | New 12.5 or 9.5mm plasterboard to be fixed to the underside of floor and roof joists, ceiling joists, rafters or suspended battens as appropriate. Allow for foil backed plasterboard where required (below roof) and for vapour-resistant plasterboard in the kitchen, bathrooms and similar.
4.5.4 |  | Provide new 12.5 or 9.5mm plasterboard surround to the services as indicated in the drawings. Allow for the associated hangers, framing and fixings. Allow for foil backed plasterboard where required (below roof) and for vapour-resistant plasterboard in the kitchen, toilets and similar.
4.6 | Stairs | Existing timber-framed staircase in the entire building to be repaired, refurbished and painted white. Allow for the aditional two top steps from the basement to ground floor following the ground floor level rising.
Total |  | Total floors, roofs, ceilings and stairs carried to summary

## 5
05. fittings, finishes and equipment
Item | Description | Cost
GENERAL:
5.1 | Internal and External finishes listed below. Contractor to provide a breakdown as suitable.
5.2 | Allow for patch repairs to the plaster following the installation of new electrical services, central heating, and gas pipework, as well as water supply and drainage runs. Repairs will also be required following the creation of new openings, insertion of new/replacement door and window frames, and where new sections of the wall are to be constructed and existing openings in-filled.
5.3 | Generally allow for final painting and decorating of all walls and ceilings - colour to client's specification.
5.4 | The maximum supply cost of all tiles and flooring indicated in the schedule below - final price to be adjusted accordingly subject to the actual supply cost. Where the supply costs of materials differ from those specified, the contractor shall present receipts and the supply cost difference shall be included in the valuations. The contractor must price for the supply, delivery and installation of all floors and tiling to include adhesive, grouting, edging, etc.
5.5 | All fittings, finishes, lighting, power sockets, equipment, etc to be supplied by the client, and installed by the contractor. Furniture and exibition panels and equipment are not part of this tender.
BASEMENT:
5.6 | Reception Room & Kitchen (RB.01), 29m² :
5.6.1 | Ceilings to be painted. Allow for two coats of paint. Colour to client specification.
5.6.2 | Walls to be painted. Allow for two coats of paint. Colour to client's specification.
5.6.3 | Fit new micro-cement flooring, supplied by the client (adhesive contractor supplied).
5.6.4 | Fit new wall and ceiling lighting as shown in the drawings. Supplied by the client.
5.6.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.6.6 | Existing staircase with balustrade to be refubrished and repaired as included in section 4. Provide quote for the finishes in this section only - to be painted white.
5.6.7 | Fit new cornices and skirting to match existing, supplied by the client.
5.6.8 | Fit new fire doors to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Supplied by the client.
5.6.9 | Fit interlinked smoke detectors, fire alarms, emergency lighting, signage, etc. to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Provided by client.
5.6.10 | Fit new suspended ceiling. Supplied by the clinet, installed by the contractor.
5.6.11 | Fit new extractor. Suplied by the contractor.
5.6.12 | Allow for 2 layers of 1h firerated plasterboard to all existing steel elements
5.6.13 | Fit 1 No. TV aerial point. supplied by the contrator.
5.6.14 | Fit 1 No. telephone point. supplied by the contractor.
5.6.15 | Existing emergancy exit ladder to be repainted
5.6.16 | Fit new air-conditioning unit
5.6.17 | Fit new radiators. Supplied by the client.
5.6.18 | Custom made terrazzo kitchen countertop 0.90x1.30m, to be cast in place by the contractor.
5.6.19 | (Note: Kitchen units/appliances to be supplied and installed by the client)
5.7 | Utility (RB.02) 2.2m²:
5.7.1 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client specification.
5.7.2 | Fit new micro-cement flooring, supplied by the client (adhesive contractor supplied).
5.7.3 | Fit new door. Supplied by the client.
5.7.4 | Fit boiler and hot water cylinder
5.7.5 | Fit new ceiling lighting. Supplied by the client.
5.7.6 | Fit new electrical sockets. Power sockets supplied by the client.
5.7.7 | Fit new extractor. Suplied by the contractor.
5.8 | Toilet (RB.03, RB.04, RB.05) 5.7m²:
5.8.1 | Walls and ceilings to be painted. Allow for two coats of paint. Colour to client specification.
5.8.2 | Fit new micro-cement flooring, supplied by the client (adhesive contractor supplied).
5.8.3 | Fit new wall tiles, supplied by the client, or water resistant toilet paint - to client’s specification (adhesive and grout contractor supplied). | TBC by client
5.8.4 | Fit new wall and ceiling lighting. Supplied by the client.
5.8.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.8.6 | Fit new doors. Supplied by client.
5.8.7 | Fit new extractor. Suplied by the contractor.
5.8.8 | Fit new washbasins. Supplied by the client.
5.8.9 | Fit new toilets. Supplied by the client.
5.8.10 | Fit new taps. Supplied by the client.
5.8.11 | Fit new toilet roll holders. Supplied by the client.
5.8.12 | Fit new mirror over basins. Supplied by the client.
5.8.13 | Fit new radiator. Supplied by the client.
5.9 | Wine Cellars (RB.06&RB.07.) 4.7& 4.8m²:
5.9.1 | Cellar vaults to be painted. Allow for two coats of paint. Colour to client specification.
5.9.2 | Fit new micro-cement flooring, supplied by the client (adhesive contractor supplied).
5.9.3 | Fit new ceiling lighting. Supplied by the client.
5.9.4 | Fit new electrical sockets. Power sockets supplied by the client.
5.9.5 | Fit new 1/2h firerated doors. Supplied by the client.
5.9.6 | Fit new extractors. Suplied by the contractor.
GROUND FLOOR:
5.10 | Exhibition space (RG.01), 31.9m²
5.10.1 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client specification.
5.10.2 | Fit new terazzo flooring, supplied by the client (adhesive contractor supplied).
5.10.3 | Refurbmishment of the existing staircase structure (timber-framed) to the first floor included in section 4. Provide quote for the finishes in this section only. Materials to client's specification.
5.10.4 | The stairwell enclosure to be upgraded to provide 30min fire resistance throughout to the final exit and all existing hallway doors to be selfclosing and to provide 30min fire resistance. Provide interlinked smoke-detectors (please see notes).
5.10.5 | Fit new fire doors to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Supplied by the client.
5.10.6 | Fit fire alarms, emergency lighting, signage, etc. to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Provided by client.
5.10.7 | Fit new entrance portal. Supplied by the client.
5.10.8 | Fit new ceiling lighting as per the drawings. Supplied by the client, installed by contractor.
5.10.9 | Repair and repaint the existing cornices and skirting. Fit new cornices and skirting (to match existing), where necessary. Supplied by the client.
5.10.10 | Fit new suspended ceiling. Supplied by the clinet, installed by the contractor.
5.10.11 | Fit new radiators. Supplied by the client.
5.10.12 | Fit new fire curtain protection within the suspended ceiling | to be quoted and installed separatly by a specialist contractor
5.10.13 | Fit steel construction for the exhibition panels as per the drawings. Supplied by the client. | to be quoted and installed separatly by a specialist contractor
5.10.14 | Fit portable vertical panels between exibition space and showroom | to be quoted and installed separatly by a specialist contractor
5.11 | Multifunctional showroom (RG.02), 11.1m2
5.11.1 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.11.2 | Fit new terazzo flooring, supplied by the client (adhesive contractor supplied).
5.11.3 | Repair and repaint the existing cornices and skirting. Fit new cornices and skirting (to match existing), where necessary. Supplied by the client.
5.11.4 | Fit new wall and ceiling lighting. Supplied by the client.
5.11.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.11.6 | Fit new rooflight, supplied by the client.
5.11.7 | Fit new radiators. Supplied by the client.
5.11.8 | Fit 2 No. speakers. Supplied by the client.
5.11.9 | Fit 1 No. telephone point. supplied by the contractor.
5.11.10 | Fit 1 No. TV aerial point. supplied by the contrator.
5.11.11 | Fit new suspended ceiling. Supplied by the client.
FIRST FLOOR:
5.12 | Landing/Staircase (RF.01), 7.9m²
5.12.1 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.12.2 | Existing hardwood flooring, staircase and balustardes to be repaired and painted white. Allow for two coats of paint. Colour to client specification.
5.12.3 | Repair and repaint the existing cornices and skirting. Fit new cornices and skirting (to match existing), where necessary. Supplied by the client.
5.12.4 | The stairwell enclosure to provide 30min fire resistance throughout to the final exit. Provide interlinked smoke-detectors (please see notes).
5.12.5 | Fit new fire door to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Supplied by the client.
5.12.6 | Fit fire alarms, emergency lighting, signage, etc. to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Provided by client.
5.12.7 | Fit new 30min. fire resistant glass partition
5.12.8 | Fit new recessed ceiling lighting. Supplied by the client, installed by contractor.
5.12.9 | Fit new radiator. Suplied by the client.
5.12.10 | Fit new toilet door. Supplied by the client.
5.12.11 | Existing window to be redecorated and refurbished.
5.12.12 | Fit new suspended ceiling. Supplied by the client.
5.13 | Toilet (RF.02), 1.6m²
5.13.1 | Ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.13.2 | Fit new terazzo flooring or floor tiles, supplied by the client (adhesive contractor supplied).
5.13.3 | Fit new wall tiles or water resistant toilet paint - to client’s specification (adhesive and grout contractor supplied). | TBC by client
5.13.4 | Fit new wall and ceiling lighting. Supplied by the client, installed by contractor.
5.13.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.13.6 | Fit new radiator. Suplied by the client
5.13.7 | Fit new washbasin. Supplied by the client.
5.13.8 | Fit new toilet. Supplied by the client.
5.13.9 | Fit new taps. Supplied by the client.
5.13.10 | Fit new toilet roll holder. Supplied by the client.
5.13.11 | Fit new extractor. Supplied by the contractor.
5.13.12 | Existing windows to be redecorated and refurbished.
5.13.13 | Fit new suspended ceiling. Supplied by the client.
5.14 | Exhibition space (RF.03), 28.3m²
5.14.1 | Fit new hardwood flooring, supplied by the client. (adhesive contractor supplied). | TBC by client
5.14.2 | Walls and Ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.14.3 | Repair and repaint all the existing decorative elements (cornices, skirting etc).
5.14.4 | Fit new ceiling lighting. Supplied by the client, installed by contractor.
5.14.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.14.6 | Fit new radiators. Suplied by the client.
5.14.7 | Existing windows to be redecorated and refurbished.
SECOND FLOOR:
5.15 | Landing/Staircase (RS.01), 7.9m²
5.15.1 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.15.2 | Existing hardwood flooring, staircase and balustardes to be repaired and painted white. Allow for two coats of paint. Colour to client specification.
5.15.3 | Repair and repaint the existing cornices and skirting. Fit new cornices and skirting (to match existing), where necessary. Supplied by the client.
5.15.4 | The stairwell enclosure to provide 30min fire resistance throughout to the final exit. Provide interlinked smoke-detectors (please see notes).
5.15.5 | Fit new fire door to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Supplied by the client.
5.15.6 | Fit fire alarms, emergency lighting, signage, etc. to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Provided by client.
5.15.6 | Fit new ceiling lighting. Supplied by the client, installed by contractor.
5.15.7 | Fit new radiator. Suplied by the client.
5.15.8 | Fit new toilet door. Supplied by the client.
5.15.9 | Fit new suspended ceiling. Supplied by the client.
5.15.10 | Existing window to be redecorated and refurbished.
5.16 | Toilet (RS.02), 1.6m²
5.16.1 | Ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.16.2 | Fit new terazzo flooring or floor tiles, supplied by the client (adhesive contractor supplied).
5.16.3 | Fit new wall tiles or water resistant toilet paint - to client’s specification (adhesive and grout contractor supplied). | TBC by client
5.16.4 | Fit new wall and ceiling lighting. Supplied by the client, installed by contractor.
5.16.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.16.6 | Fit new radiator. Suplied by the client
5.16.7 | Fit new washbasin. Supplied by the client.
5.16.8 | Fit new toilet. Supplied by the client.
5.16.9 | Fit new taps. Supplied by the client.
5.16.10 | Fit new toilet roll holder. Supplied by the client.
5.16.11 | Fit new extractor. Supplied by the contractor.
5.16.12 | Existing windows to be redecorated and refurbished.
5.16.13 | Fit new suspended ceiling. Supplied by the client.
5.17 | Meeting/Presentation room, (RS.03), 29.1m²
5.17.1 | Fit new hardwood flooring, supplied by the client. (adhesive contractor supplied). | TBC by client
5.17.2 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.17.3 | Repair and repaint all the existing decorative elements (cornices, skirting etc).
5.17.4 | Fit new ceiling lighting. Supplied by the client, installed by contractor.
5.17.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.17.6 | Fit new radiators. Suplied by the client.
5.17.7 | Existing windows to be redecorated and refurbished.
5.17.8 | Fit new airconditioning unit. Supplied by the client.
THIRD FLOOR:
5.18 | Landing/Staircase (RT.01), 6.5m²
5.18.1 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.18.2 | Existing hardwood flooring, staircases and balustardes to be repaired and painted white. Allow for two coats of paint. Colour to client specification.
5.18.3 | Repair and repaint the existing cornices and skirting. Fit new cornices and skirting (to match existing), where necessary. Supplied by the client.
5.18.4 | The stairwell enclosure to provide 30min fire resistance throughout to the final exit. Provide interlinked smoke-detectors (please see notes).
5.18.5 | Fit new fire doors to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Supplied by the client.
5.18.6 | Fit fire alarms, emergency lighting, signage, etc. to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Provided by client.
5.18.7 | Fit new suspended ceiling. Supplied by the client.
5.18.8 | Fit new ceiling lighting. Supplied by the client, installed by contractor.
5.18.9 | Fit new radiator. Suplied by the client.
5.18.10 | Existing balustrades to be retained and covered with plasterboard, as specified in the drawings.
5.19 | Working space (RT.02), 28.3m²
5.19.1 | Fit new hardwood flooring, supplied by the client. (adhesive contractor supplied). | TBC by client
5.19.2 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.19.3 | Repair and repaint all the existing decorative elements (cornices, skirting etc).
5.19.4 | Fit new ceiling lighting. Supplied by the client, installed by contractor.
5.19.5 | Fit new electrical sockets. Power sockets supplied by the client.
5.19.6 | Fit new radiators. Suplied by the client.
5.19.7 | Existing windows to be redecorated and refurbished.
5.19.8 | Fit new airconditioning unit. Supplied by the client.
LOFT:
5.20 | Working area (RL.01), 27.7m²
5.20.1 | Fit new hardwood flooring, supplied by the client. (adhesive contractor supplied). | TBC by client
5.20.2 | Walls and ceiling to be painted. Allow for two coats of paint. Colour to client's specification.
5.20.3 | Fit fire alarms, emergency lighting, signage, etc. to comply with Part B (Fire safety) of the building regulations and the LFB requirements. Provided by client.
5.20.4 | Fit new skirting to match existing, supplied by the client.
5.20.5 | Fit mdf covering as specified in the drawings, on the ceiling and around the existing balustrade.
5.20.6 | Fit new wall and ceiling lighting. Supplied by the client, installed by contractor.
5.20.7 | Fit new electrical sockets. Power sockets supplied by the client.
5.20.8 | Fit new radiators. Suplied by the client.
5.20.9 | Fit new airconditioning unit. Supplied by the client.
5.20.10 | Existing front window to be redecorated and refurbished.
5.20.11 | Fit new rear window and roof exit door. Supplied by the client.
5.20.12 | Fit new glazed roof. Supplied by the client, installed by the contractor.
5.20.13 | Fit 1 No. TV aerial point. supplied by the contrator.
5.20.14 | Fit 1 No. telephone point. supplied by the contractor.
5.21 | EXTERNAL FINISHES
5.21.1 | Allow for existing front façade to be cleaned - jet washed
5.21.2 | Repair the existing fascia on front façade
5.21.3 | Allow for external bulkhead light fitting and sensors and fascia downlighters as indicated in the drawings. Supplied by the client.
5.21.4 | Fit external/internal security cameras as indicated in the drawings. Supplied by the client.
5.21.5 | Fit bin store. Supplied by the client.
CONTRACTOR TO PROVIDE BREAKDOWN BELOW AND SPECIFY PROVISIONAL ITEMS BELOW
Total fittings and finishes carried to summary

## 6
06. Windows and Doors
Ref. | Room | Opening Size | New / Existing | Window / Door Type | Comments | Cost
FRONT ELEVATION WINDOWS
DE.01 | Exhibition space/Ground floor | Existing | New | Timber Framed- Single glazed painted black to match the original window-conservation style . (shopfront with entrance doors) | Special item. To be supplied and detailed by the window specialist chosen by the contractor and the architect, and approved by the local authority. Contractor to pick the item up individually and provide either a provisional sum or a lump sum. | SUPPLIED BY CLIENT.
WF.01 | Exhibition space/ First Floor | Existing | Existing | Timber Framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.01 | Meeting& Presentation room / Second Floor | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.02 | Meeting& Presentation room / Second Floor | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.03 | Meeting& Presentation room / Second Floor | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WT.01 | Working space / Third floor | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WT.02 | Working space / Third floor | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WT.03 | Working space / Third floor | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WL.01 | Working space / Loft | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WL.02 | Working space / Loft | Existing | New | Timber Framed Dormer Window | Single glazed painted white to match the original window | SUPPLIED BY CLIENT.
REAR ELEVATION WINDOWS
WF.02 | Exhibition space | Existing | Existing | Timber Framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WF.03 | Hallway | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WF.04 | Toilet | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WF.05 | Toilet | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.02 | Meeting/ Presentation room | Existing | Existing | Timber Framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.03 | Hallway | Existing | Existing | Timber Framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.04 | Toilet | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WS.05 | Toilet | Existing | Existing | metal framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WT.04 | Working area/ Third floor | Existing | Existing | Timber Framed | existing windows to be retained, redecorated and refurbished only | INCLUDED
WL.03 | Working area/ Loft | Existing | New | Timber Framed | Double glazed painted white to match the original window. | SUPPLIED BY CLIENT.
ROOF WINDOWS
WR.01 | Flat Roof | Existing (approx.1000x 1400mm) | New | uPVC | Velux or similar flat dome Roof light | SUPPLIED BY CLIENT.
WR.02 | Main roof | Existing | TBC | Conservation style Glass roof, timber framed, colour white | Existing glazed roof to be retained and repaired. If replacement is necessary, new conservation style timber framed glazed roof to be installed, to match existing. Generally allow for all associated motorised blinds, flashings, fixings etc. | SUPPLIED BY CLIENT.
BASEMENT DOORS
DB.01 | Utility | 800x2100 | New | metal framed | metal framed, black frame with mirror panel door | SUPPLIED BY CLIENT.
DB.02 | Toilet | 800x2100 | New | metal framed | metal framed, black frame with mirror panel door | SUPPLIED BY CLIENT.
DB.03 | Toilet | 700x2000 | New | Veneered | Veneered single door painted white | SUPPLIED BY CLIENT.
DB.04 | Toilet | 700x2000 | New | Veneered | Veneered single door painted white | SUPPLIED BY CLIENT.
DB.05 | Wine cellar | 1000x1700 (tbc on site) | new | Hardwood | Hardwood single fire door with 30 minutes protection w. intumescent strips; | SUPPLIED BY CLIENT.
DB.06 | Wine cellar | 1000x1600 (tbc on site) | new | Hardwood | Hardwood single fire door with 30 minutes protection w. intumescent strips; | SUPPLIED BY CLIENT.
GROUND FLOOR DOORS
DG.01 | Exhibition space | 950x2100 | New | Hardwood | Hardwood single door with recessed glazed panels, painted white. Fire door with 30 minutes protection w. intumescent strips | SUPPLIED BY CLIENT.
FIRST FLOOR DOORS
DF.01 | Exhibition space | existing | New | Hardwood | Hardwood single door with glazed panel; Fire door with 30 minutes protection w. intumescent strips | SUPPLIED BY CLIENT.
DF.02 | Toilet | existing | New | Hardwood | Hardwood single door with recessed panels | SUPPLIED BY CLIENT.
DF.03 | Exhibition space | existing | New | Hardwood | fixed glass partition, 30min. fire resistant | SUPPLIED BY CLIENT.
SECOND FLOOR DOORS
DS.01 | Meeting/ Presentation room | existing | New | Hardwood | Hardwood single door with glazed panel; Fire door with 20 minutes protection w. intumescent strips | SUPPLIED BY CLIENT.
DS.02 | Toilet | existing | New | Hardwood | Hardwood single door with recessed panels | SUPPLIED BY CLIENT.
THIRD FLOOR DOORS
DT.01 | Working space | existing | New | Hardwood | Hardwood single door with glazed panel; Fire door with 30 minutes protection w. intumescent strips | SUPPLIED BY CLIENT.
DT.02 | Hallway | existing | New | Hardwood | Hardwood single door with glazed panel; Fire door with 30 minutes protection w. intumescent strips | SUPPLIED BY CLIENT.
Total doors and windows carried to summary

## 7
07. services
Item | Description | Cost
7.1 | Disposal Installations
7.2 | Internal Drainage
7.2.1 | Internal Foul Drainage Pipework Generally to kitchens, utility and W.Cs
7.2.2 | Completion Of Design Of Above Ground Foul Drainage System by the specialist sub-contractor including selection of appropriate preformed joints, junctions, fittings and fixings throughout.
7.2.3 | Internal Foul Drainage Discharge Stacks And Branches Generally.
7.2.4 | Plastics Waste Pipes And External Plastics SVP.
7.2.5 | Completion Of Design Of Above Ground Foul Drainage System including selection of appropriate preformed joints, junctions, rodding points, fittings and fixings throughout.
7.2.6 | PVCU Soil And Vent Pipework.
7.2.7 | MUPVC Or PVCC Waste Pipework.
7.3 | Water Installations
7.3.1 | Mains Cold Water System and hot water pipes - provide stop cocks and isolating values. Liaise with the utility company to provide an adequate connection.
7.3.2 | Complete the design and detailing of the water supply installation to BS 6700.
7.3.3 | Thermoplastics Pipelines For Hot and cold Water System
7.3.4 | Copper Pipelines For Hot And Cold Water System
7.3.5 | Pipeline Insulation For Hot And Cold Water System
7.3.6 | Flow Reducing And Servicing Valves For Hot And Cold Water System
7.4 | Hot Water Services
7.4.1 | Supply and fit the hot water pipework
7.4.2 | Supply and fit the new boiler to be installed in the utility
7.5 | Water Central Heating
7.5.1 | Gas boiler for central heating and hot water.
7.5.2 | Completion of heating design by contractor as specified in the schedule to achieve the design parameters.
7.5.3 | Provide a new gas fired central heating boiler(s)
7.5.4 | Unvented Hot Water Storage.
7.5.5 | Fused Connection Unit.
7.5.6 | Plastics Conduit And Fittings.
7.5.7 | Copper Pipeline For Gas Supply To Heating System.
7.5.8 | Bypass Valve and Pump overrun For Hot Water Heating.
7.5.9 | Test and balance whole heating and hot/ cold water supply systems.
7.5.10 | Warning And Overflow Pipes To Cisterns For Hot And Cold Water System.
7.5.11 | Provide Radiators to all floors (except basement) as specified in the drawings
7.6 | Ventilating System | to be quoted separately
7.6.1 | New Extract Fan and extract ductwork to new toilets, utility etc.
7.6.2 | Ventilation Fan Unit Wall Mounted with fan, associated ductwork and external grille. Operated by light switch. Integral humidity sensor with switch override
7.6.3 | Ventilation Fan Controller Manual Operation w. On/ off switching, fan speed and airflow direction.
7.6.4 | External Ventilation Grille
7.6.5 | Forming Opening In Existing Brick And Concrete Block Cavity Wall
7.6.6 | Fused Connection Unit
7.7 | Electrical Installations
7.7.1 | Electric Power Supplies:
7.7.2 | New Electrical Installation Complete As Drawings to the building as specified in the drawings. Allow for the extension and loft to be wired. Select an appropriate head and meter location into the smallest configuration for enclosure. Run cables to locations identified in the specification of the works. Supply and fit switches, sockets TV and telephone points etc.
7.7.3 | Distribution Boards And Consumer Units. New distribution boards to be adequate to accommodate the building and link light, heating and plant.
7.7.4 | Electrical Accessories where not visible
7.7.5 | Separate spur to supply power to the sockets in the kitchen.
7.7.6 | Standard Socket Outlets. All power sockets to be supplied by the client to be installed by the contractor.
7.7.7 | Fused Connection Unit For appliances under kitchen units local to appliances.
7.7.8 | Cooker Double Pole Switch Position inside kitchen units.
7.7.9 | Supply all documentation to Architect copy to Client.
7.7.10 | Provide electrical under floor heating as specified in the drawings.
7.8 | Electric Lighting
7.8.1 | Contractor Designed Electrical Lighting Installation. Refer to drawings for the position and number of electrical sockets and lights. All light fixtures and fittings incl. switches to be supplied by the client and installed by the contractor
7.8.2 | Design And Detailing - The drawings show the outline design and layout of the main components of the electrical system. Complete the design, detailing, selection, installation and testing and commissioning of the electrical systems.
7.8.3 | Inspection And Testing Of Electrical System
7.8.4 | Inspection And Testing Of External Lighting System
7.8.5 | Documentation - Full technical description of each system installed. Manufacturer's operating and maintenance instructions for fittings and apparatus. Manufacturer's guarantees and warranties. As-installed drawings showing circuits and their ratings and locations of fittings and apparatus. List of normal consumable items.
7.8.6 | Commissioning Of Electrical System.
7.8.7 | External Electric Lighting Circuit.
7.8.8 | Please see drawings for more information. Detailed design to be submitted by the electrical subcontractor.
7.8.9 | Inspection And Testing Of External Lighting System.
7.9 | Electric Light Fittings
7.9.1 | Light fittings - Refer to drawings for the position and number of fittings - all light fittings to be supplied by the client and installed by the contractor.
7.10 | Gas Installations
7.10.1 | Gas installation to kitchen and boilers to include pipes for the gas hobs and boilers. Existing pump to be relocated.
7.11 | Communication Installations
7.12 | Warning Installations
7.12.1 | Smoke Alarm Circuit as shown on the drawings and also in compliance with the regulations and Fire Officer recommendations
7.13 | Builder's Work In Connection With Services
7.13.1 | Allow for Builders work in connection with services.
7.13.2 | Allow for Builders work (excavation, backfilling, compaction of soil) to install new below-ground drainage and other services as shown in the drawings. Also allow for making good the walls/floors/ceiling following the installation of new services as well as any other builders work associated with the services. | TBC
7.14 | Below ground services | TBC
7.15 | External drainage
7.15.1 | Supply and install new round down pipes for drainage of the pitched and flat roof of the extensions. Include all necessary flashing elements, etc. where required.
7.15.2 | Supply and install new round down pipes for drainage of the existing dormer window. Include all necessary flashing elements, etc. where required.
Total services and fittings carried to summary